## Tutorial Ninja
BUG ID | Description | Steps To Reproduce | Expected Result | Actual Result | Severity | Priority | ScreenShot
BUG_001 | In the register page, when a user enters a number in the full name section. | 1. Open the Register page. 2. Enter numbers in the Full Name field. 3. Click Register. | The system should show an error that the name cannot contain numbers. | The system allows registration even when the name contains digits. | High (Validation issue) | Medium
BUG_002 | In the mobile number section, the user enters an invalid number or alphabets. | 1. Go to Register page. 2. Enter any number shorter or longer than 10 digits in Phone Number. | Should show a validation message that phone number must be exactly 10 digits. | Registration completes successfully without validation. | High | High
BUG_003 | After login, the username is missing in the top-right corner. | 1. Go to the login page. 2. Enter valid credentials. 3. Click the "Login" button. | Logged-in username should appear on top-right. | Username is not displayed anywhere after login. | Medium | Medium
BUG_004 | The search section does not display appropriate results. | 1. Use search bar. 2. Search for “Laptop” or “Camera”. | Relevant search results should appear. | Only results for “iPhone” are shown, other searches return nothing. | High | High
BUG_005 | Product information is incomplete in some sections. | 1. Click on a product (e.g., laptop or mobile). | The user should see complete product information, including specifications. | The product information is incomplete or missing in some sections. | Medium | Medium
BUG_006 | Category dropdown does not expand on first click (requires double click). | 1. Hover over "Desktops" in the top menu. 2. Click the dropdown arrow. | The submenu should open on a single click. | In some cases, the dropdown does not expand on first click and requires clicking twice. | Medium | Medium
BUG_007 | Rating section is not functional. | 1. Click on the rating section of a product. | The rating section should function properly, allowing users to rate the product. | The rating section does not work. | Low | Low
BUG_008 | Related products are not shown in specific sections. | 1. Click on a dropdown menu. 2. Select a specific product section. | Related products should appear in the specific section. | Random products appear instead of related ones. | High | High
BUG_009 | The website logo is missing from the top-left corner. | 1. Open the browser. 2. Enter the website URL. | The website logo should appear in the top-left corner. | The website logo is missing. | Medium | Medium
BUG_010 | Unnecessary information is displayed in the product section. | 1. Click on the product section. | Only relevant information should be displayed. | Unnecessary information (e.g., unrelated data) is shown. | Medium | Medium
BUG_011 | Related products are missing in the product information section. | 1. Click on the product section. 2. Open product information. | Related products should appear in the product information section. | Related products are missing for some items (e.g., "Camera"). | Medium | Medium
BUG_012 | Number entry is accepted in the billing name section. | 1. Add a product to the cart. 2. Proceed to checkout. 3. Enter a number in the name section of the billing form. | An error message should display stating only alphabets are allowed. | No error is displayed, and the form is submitted successfully. | Medium | Medium
BUG_013 | "Add to cart" button is functional for out-of-stock products. | 1. Select a product that is out of stock. 2. Click "Add to cart". | The "Add to cart" button should be disabled for out-of-stock products. | The "Add to cart" button is functional. | Low | Low
BUG_014 | Image quality is poor across the website. | 1. Open the browser. 2. Enter the website URL. 3. Browse through the products. | Images should be high quality. | Images are of poor quality. | Low | Low
BUG_015 | Pincode field accepts empty input. | 1. Add a product to the cart. 2. Proceed to checkout. 3. Leave the pincode field empty. 4. Submit the form. | An error message should appear stating "Pincode is required". | The form is submitted without a pincode. | High | High
BUG_016 | Missing company information in the "About" section. | 1. Go to the "About" section. | The section should display detailed company information. | No data is displayed in the "About" section. | Medium | Medium
BUG_017 | "Cancel Order" option is missing. | 1. Place an order. 2. Go to the order details page. | A "Cancel Order" button should be available. | The "Cancel Order" option is missing. | Medium | Medium
BUG_018 | Multiple login attempts are allowed without a captcha. | 1. Enter invalid credentials multiple times. | After a few attempts, a captcha should appear to prevent bots. | No captcha is displayed, allowing unlimited login attempts. | High | High
BUG_019 | Weak password validation | 1. Go to the login section. 2. Fill in valid credentials. 3. Click the "Login" button. | Password fields should not accept less than six characters. | Password fields accept less than six characters. | Critical | Needs Review
BUG_020 | Plaintext passwords in reset emails | 1. Go to the login section. 2. Click on Forgotten Password 3. Enter email in email section | Passwords will not sent in plaintext in "Forgot Password" emails. | Passwords sent in plaintext in "Forgot Password" emails. | Critical | Needs Review
BUG_021 | Product comparison does not display proper specs | 1. Compare two products (e.g., MacBook and iPhone). | Comparison table should show correct specifications. | Comparison table shows incomplete or mismatched data. | Medium | Medium
BUG_022 | Search allows XSS input | 1. Enter <script>alert(1)</script> in search bar. 2. Press Enter. | Input should be sanitized and treated as plain text. | Script executes or displays broken page layout. | Critical | High
BUG_023 | Price filter slider not functional | 1. Go to a product category. 2. Use price filter slider to narrow results. | Results should filter based on selected price range. | Slider has no effect on displayed results. | Medium | High
BUG_024 | Image zoom not working on product details page | 1. Open any product page. 2. Hover over product image. | Image should zoom in for better view. | Zoom function does not work. | Low | Medium
BUG_025 | “Newsletter Subscription” accepts empty input | 1. Scroll to footer. 2. Leave email field blank and click Subscribe. | Should show validation error for empty input. | Submits successfully with no email entered. | Medium | High

## Release Note
Project Name: Tutorial Ninja Demo Website Version Tested: v1.0 (Public Demo) Tested By: Ariha Zainab Date: October 2025 Test Environment: Browser: Google Chrome (Latest Version) OS: Windows 10 Device: Desktop Summary: I performed exploratory testing on the Tutorial Ninja demo e-commerce website to check the core features like login, registration, product search, product details, cart, and checkout. During testing, I found several issues in validation, UI behavior, and security flow. Search and checkout modules showed the most inconsistent behavior. Defect Overview: Critical Bugs: 3 (Weak password validation, Plaintext passwords in reset emails, XSS vulnerability in search bar) High Severity Bugs: 6 (Mobile number validation, Search issues, Pincode field empty acceptance, Multiple login attempts without captcha, Contact Us form invalid email) Medium Severity Bugs: 12 (Missing username after login, Product info incomplete, Category dropdown issues, Related products missing, Website logo missing, Billing name accepts numbers, About section missing info, Cancel order option missing, Product comparison incomplete, Price filter slider not functional, Continue Shopping redirects incorrectly, Footer links redirect to 404 pages) Low Severity Bugs: 4 (Rating section not functional, Add to Cart works for out-of-stock products, Image quality poor, Image zoom not working) Overall Status: Build Not Stable for Production The application contains significant security and functional issues that must be resolved before release. Validation checks, payment features, and user experience elements require urgent fixes. Recommendations: Add proper client-side and server-side validations (names, phone numbers, passwords, etc.). Fix checkout and payment flow to prevent incorrect form submissions. Improve product search to return consistent and relevant results. Ensure password reset functions do not expose credentials. Improve UI layout consistency and error message visibility.